## Sheet1
The Shadow IT Register is the operational governance instrument for managing the population of assets discovered outside the governed provisioning process. It is not a finding list — it is a lifecycle management tool that tracks each shadow asset from discovery through resolution.
SHADOW IT REGISTER — FIELD SCHEMA AND GOVERNANCE WORKFLOW
DISCOVERY FIELDS
Shadow Asset ID
System-generated: SHADOW-YYYY-NNNN
Discovery Date
Date first detected
Discovery Method
CASB / Expense Report / Cloud Enum / DNS Analysis / Network Traffic / Employee Report / Other
Asset Description
Resource type, name, location —what was found and where?
Discovered By
Analyst name and tool reference
RISK STRATIFICATION FIELDS
Risk Level
Level 1 / Level 2 / Level 3
Level 1 Criteria:
Productivity tool; No regulated data indicators: Small user population; No external sharing
Level 2 Criteria:
Business process application; Possible regulated data; Significant user population; OR any integration with corporate systems
Level 3 Criteria:
Demonstrable regulated data (PHI/CHD/PII); Privileged access to corporate systems; Internet-facing without security controls; OR cloud environment with production workloads
Risk Stratification Rationale:
Specific criteria met — document which Level criteria triggered this classification
Automated Indicators Present:
☐ Public internet exposure detected
☐ Regulated data type keyword in resource name/tags
☐ Storage resource (bucket/blob/drive)
☐ Integration with corporate identity provider detected
☐ Production account environment
☐ Data volume above threshold (>1GB)
OWNERSHIP RESOLUTION FIELDS
Probable Business Unit:
From automated attribution: account owner / cost center / creating identity
Ownership Query Sent
[Date + recipient]
Ownership Response:
Date + responder name
Claimed Owner:
Named individual + title + BU
Owner Designation Date:
Date ownership formally confirmed
Escalation Level:
None / Manager / Executive / CISO+Legal
Escalation Date:
If applicable
Escalation Response:
Outcome of escalation
GOVERNANCE RESPONSE FIELDS
Response Track:
ADOPT — enter governance program /
REMEDIATE — modify to meet standards /
DECOMMISSION — retire the asset /
ISOLATE — immediate containment (Level 3)]
For ADOPT Track:
Fast Lane Eligible:
YES/NO — is this application already in the approved catalog?
Security Assessment Required:
YES/NO
Assessment Status:
Not Started / In Progress / Complete
Assessment Date:
Date completed
Assessment Finding:
Pass / Conditional Pass / Fail
DPA Required:
YES/NO
DPA Status:
Not Required / Requested / Executed
RoPA Entry Required:
YES/NO — GDPR personal data present
RoPA Status:
Not Required / Pending / Complete
BAA Required:
YES/NO — PHI present + HIPAA applies
BAA Status:
Not Required / Requested / Executed
Asset Register Entry Created:
Date
Governance Completion Date:
Date all required items closed
For DECOMMISSION Track:
Decommission Deadline:
Date
Data Disposition Method:
Export / Delete / Archive
Data Disposition Complete:
Date + evidence reference
Decommission Confirmed:
Date + confirming analyst
For ISOLATE Track (Level 3 only):
Isolation Recommended:
Date + analyst recommendation
Isolation Decision:
CISO decision + date
Legal Notified:
Date
Regulatory Breach Assessment:
Triggered: YES/NO
Breach Assessment Status:
In Progress / Complete / No Breach / Breach Confirmed
TIMELINE AND SLA FIELDS
Required Resolution Date:
Level 1: 30 days / Level 2: 30 days for owner designation, 30 additional days for governance / Level 3: 48 hours for initial response
Current Status:
On Track / At Risk / Overdue
Days Until Deadline:
Calculated field
Days Overdue:
Calculated field — if applicable
Next Required Action:
Specific next step
Action Owner:
Named individual responsible
Action Due Date:
Specific date
PREVENTION FLAGS
Root Cause Category:
No provisioning gate / Fast Lane gap / Procurement bypass / Developer workaround / Legacy system / Vendor-initiated / Unknown
Prevention Recommendation:
Specific structural change to prevent recurrence of this category
Prevention Action Status:
Pending / In Progress / Complete
AUDIT TRAIL
Immutable timestamped log of every status change, action taken, communication sent, decision made, and individual responsible — append-only, no deletions
SHADOW IT REGISTER — EXECUTIVE SUMMARY DASHBOARD
(Auto-generated from register data — refreshed daily)
CURRENT POPULATION:
Total Active Shadow Assets: ___
Level 1: ___
Level 2: ___
Level 3: ___
RESOLUTION STATUS:
On Track: ___ (___%)
At Risk: ___ (___%) [<7 days to deadline, action pending]
Overdue: ___ (___%) [Past required resolution date]
LEVEL 3 ITEMS (IMMEDIATE ATTENTION REQUIRED):
[Listed individually with current status and days active]
GOVERNANCE COMPLETIONS (LAST 30 DAYS): ___
ROOT CAUSE DISTRIBUTION:
No provisioning gate: ___
Fast Lane gap: ___
Procurement bypass: ___
Developer workaround: ___
PREVENTION ACTIONS PENDING: ___