## Sheet1
IAM Risk Register
A structured inventory of IAM risks — each defined with a description, likelihood, impact, current controls, residual risk, and remediation plan. The Risk Register is the bridge between the IAM program and enterprise risk management — it translates IAM control status into the language the CRO and board use to make risk decisions.
Risk ID | Risk Description | Likelihood (1-5) | Impact (1-5) | Inherent Risk | Current Controls | Control Effectiveness | Residual Risk | Remediation Plan | Owner | Target Date
IAM-001 | Unauthorized access to financial systems due to SoD violations | 3 | 5 | High | SoD conflict detection in SAP GRC; quarterly remediation review | Partial — 23 active unmitigated conflicts | High | Remediate top 10 conflicts by Q3; implement preventive SoD enforcement | IAM Director | Q3 2025
IAM-002 | Account takeover via AiTM phishing targeting push notification MFA | 4 | 5 | Critical | Push notification MFA at 91% coverage; SIEM alerting for auth anomalies | Partial — push MFA does not defend against AiTM; alerting not tuned for token replay | Critical | Deploy FIDO2 for privileged population by Q2; deploy AiTM detection rules by Q1 | CISO | Q2 2025
IAM-003 | Pesistent vendor access post-contract termination | 3 | 4 | High | Vendor acces review semi-annually; contract termination checklist | Weak - manual process; 14% of vendors found with access beyond contract end in last review | High | Automate vendor access expiration tied to contract end date in IGA platform | IAM Operations | Q1 2025
IAM-004 | Helpdesk social engineering enabling MFA bypass | 4 | 5 | Critical | Knowledge-based identity verification for helpdesk requests | Weak-OSINT-defeatable verification; no adversarial testing conducted | Critical | Implement out-of-band device verification for all MFA resets; conduct red team helpdesk simulation | IAM Director | Q1 2025